# IncuBrix 30-Day Social Launch Kit

# Executive summary

Prepare a proof-led content program for podcasters, YouTubers, expert-led creators, editors, and small content teams. Publish across LinkedIn, Instagram, YouTube Shorts, X, and Threads. Every post carries an asset-level UTM. The first week establishes a baseline; all targets below are assumptions to reset after real data exists.

# Audience and geography

Primary audience: solo and 1–5 person teams already producing long-form audio or video at least monthly and struggling to repurpose it consistently. Buyers and influencers include creators, editors, content managers, coaches, and founders. Priority regions: United States, Canada, United Kingdom, Ireland, Australia, New Zealand, and Singapore.

# Platform strategy

| Platform | Role | Why | Starting cadence |
| --- | --- | --- | --- |
| LinkedIn | Primary | Expert creators, founders, and saveable carousels | 5/week |
| Instagram | Primary | Reels and carousel-native creator education | 4/week |
| YouTube Shorts | Primary | Natural extension of long-form back catalogues | 3/week |
| X | Experiment | Fast hook and copy testing | 5/week |
| Threads | Experiment | Low-production conversation and reposting | 3/week |

Keep the best two channels by qualified clicks per post after enough comparable posts exist. Do not call a platform a failure from one post.

# Content pillars and voice

Hooks and openings — earn the first two seconds.

Captions and editing craft — trims, safe areas, and readable copy.

Repurposing playbooks — turn one source into several useful formats.

Creator workflow — batching, approval, measurement, and iteration.

Trust and rights — consent, source preservation, and transparent AI use.

Voice: practical, creator-to-creator, specific, short sentences, no guarantees, no unsupported statistics, and one action per post. Product features remain Draft until verified with evidence.

# Content-to-signup path

Useful post → one CTA → asset-specific UTM link → landing page → signup. UTMs use utm_source, utm_medium=organic_social, campaign, asset ID in utm_content, and pillar in utm_term. Confirm that the signup system retains these fields before claiming social-attributed signups.

# 30-day calendar

The complete 40-row draft calendar is 30_Day_Content_Calendar.csv. It includes date, platform, asset, pillar, hook, caption, CTA, link, time, owner, and target/actual fields. It spans 2026-11-02 through 2026-12-01. Every row is pending human rights, brand, editorial, account, and publication approval. Dates are a planning template; the candidate must confirm the actual launch date.

# First Monday

09:00 — confirm product/account access, owner, approver, and launch date.

09:30 — verify product claims; unsupported claims remain Draft.

10:30 — confirm landing-page UTM persistence with one test conversion.

11:00 — inspect the first seven scheduled posts, media crops, and links.

13:00 — approver records signoff; do not publish unauthorized branding.

Scheduled slot — publish only if the first asset is explicitly approved.

Within 24 hours — reply to genuine comments and record the public URL.

# Operating workflows

Daily: check due rows, preview the post, obtain approval, publish, verify the link, respond within 24 hours, and log the URL. After a consistent 48-hour window, record reach, interactions, clicks, and signups if attribution exists.

Weekly: run one new input, review claims/rights, approve the batch, compare like-for-like posts, document keep/change/stop decisions, and update the next week. Never delete weak results.

# Owners and tools

| Role | Responsibility | Assumption |
| --- | --- | --- |
| Growth owner | Engine, calendar, publishing, community, report | Candidate or named IncuBrix owner — pending confirmation |
| Approver | Claims, copy, brand, rights, final release | Founder/marketing lead — pending |
| Creator/founder | One original screen/voice asset weekly | Pending |
| Analytics owner | UTM persistence and signup report | Pending |

Tools: Python engine, FFmpeg, Pillow, native platform schedulers, spreadsheet, and IncuBrix publishing only after signed-in verification.

# Budget assumptions

Offline engine, fonts, and native scheduling: USD 0 direct run cost. Optional paid test budget: USD 0 by default; up to USD 200 in weeks 3–4 only with written approval and only on the best proven organic post. Candidate AI subscription costs are pending disclosure.

# Planning targets

| Metric | 30-day assumption | Measurement |
| --- | --- | --- |
| Posts | 40 delivered assets; scale toward 80 only if capacity permits | Public URLs |
| Reach | 40,000 total | Native impressions/views by asset |
| Median engagement | ≥3% primary channels | Consistent interactions ÷ impressions |
| Link clicks | 200 | UTM report by asset |
| Signups | 20 only if UTM capture works | Signup records retaining source/content |

These are forecasts, not results. Reset them after week-one baseline data.

# KPI review and reporting

Report posts, reach, median engagement, clicks/post, click-through rate, and signups where attribution exists. Segment by platform, pillar, format, and hook. Keep observation windows consistent. The public LinkedIn follower-based proxy in the competitor audit is not a full engagement rate.

# Approval and compliance

Technical draft → growth review → claim check → rights/brand check → platform preview → approver signoff → schedule → post verification. Required checks: source traceability, no unsupported feature claim, no third-party media without permission, no private data, appropriate AI label, correct crop/duration, working UTM, authorized brand treatment, and one CTA.

# Risk register

| Risk | Owner | Mitigation | Trigger |
| --- | --- | --- | --- |
| Generic text-only creative | Growth | Add original screen/voice proof weekly | Two posts below baseline |
| Unsupported claim | Approver | Evidence-linked claim register and Draft hold | Any feature wording |
| Rights or privacy issue | Approver | Written consent/license and no private data | Missing evidence |
| UTM loss | Analytics | Test before launch; report clicks only if signup source is lost | Click with no attribution |
| Platform change | Growth | Recheck help guidance monthly | Crop/rejection warning |
| Low reach | Growth | Consistency, real replies, no purchased engagement | Week-one miss |
| Provider outage/unsafe AI | Engineer | Offline default and validation | AI error or failed trace |

# End-of-month decision

Continue channels with repeatable qualified clicks and manageable production; change weak hooks/formats with a documented hypothesis; stop channels that show repeatedly weak signal after comparable tests. Report uncertainty and all results, including zeroes.

# Appendix: 30-day asset calendar

Planning dates and targets only. Every row remains pending human approval; actual-result fields are blank.

| Date | Platform | Asset | Pillar | UTC | Status | Targets: reach / engagement / clicks / signups |
| --- | --- | --- | --- | --- | --- | --- |
| 2026-11-02 | LinkedIn | EORC57-C01 | Repurposing playbooks | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-02 | Instagram | EORC57-C02 | Hooks and openings | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-03 | LinkedIn | EORC57-C03 | Creator workflow | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-03 | Instagram | EORC57-C04 | Trust and rights | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-04 | LinkedIn | EORC57-G01 | Captions and editing craft | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-04 | Instagram | EORC57-G02 | Repurposing playbooks | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-05 | X | EORC57-G03 | Repurposing playbooks | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-05 | Threads | EORC57-G04 | Repurposing playbooks | 18:00 | Pending human approval | 500 / 2.0% / 2 / 0 |
| 2026-11-06 | LinkedIn | EORC57-T01 | Repurposing playbooks | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-06 | X | EORC57-T02 | Creator workflow | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-07 | Threads | EORC57-T03 | Creator workflow | 18:00 | Pending human approval | 500 / 2.0% / 2 / 0 |
| 2026-11-07 | LinkedIn | EORC57-T04 | Repurposing playbooks | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-08 | Instagram | EORC57-V01 | Captions and editing craft | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-08 | YouTube Shorts | EORC57-V02 | Hooks and openings | 16:00 | Pending human approval | 1800 / 2.5% / 7 / 1 |
| 2026-11-09 | LinkedIn | EORC57-V03 | Hooks and openings | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-09 | X | EORC57-V04 | Captions and editing craft | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-10 | Instagram | EORC57-V05 | Hooks and openings | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-10 | YouTube Shorts | EORC57-V06 | Trust and rights | 16:00 | Pending human approval | 1800 / 2.5% / 7 / 1 |
| 2026-11-11 | LinkedIn | EORC57-V07 | Creator workflow | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-11 | X | EORC57-V08 | Hooks and openings | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-12 | LinkedIn | ETH2D2-C01 | Hooks and openings | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-13 | Instagram | ETH2D2-C02 | Hooks and openings | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-14 | LinkedIn | ETH2D2-C03 | Captions and editing craft | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-15 | Instagram | ETH2D2-C04 | Creator workflow | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-16 | LinkedIn | ETH2D2-G01 | Captions and editing craft | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-17 | Instagram | ETH2D2-G02 | Captions and editing craft | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-18 | X | ETH2D2-G03 | Hooks and openings | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-19 | Threads | ETH2D2-G04 | Hooks and openings | 18:00 | Pending human approval | 500 / 2.0% / 2 / 0 |
| 2026-11-20 | LinkedIn | ETH2D2-T01 | Hooks and openings | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-21 | X | ETH2D2-T02 | Hooks and openings | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-22 | Threads | ETH2D2-T03 | Captions and editing craft | 18:00 | Pending human approval | 500 / 2.0% / 2 / 0 |
| 2026-11-23 | LinkedIn | ETH2D2-T04 | Captions and editing craft | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-24 | Instagram | ETH2D2-V01 | Captions and editing craft | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-25 | YouTube Shorts | ETH2D2-V02 | Hooks and openings | 16:00 | Pending human approval | 1800 / 2.5% / 7 / 1 |
| 2026-11-26 | LinkedIn | ETH2D2-V03 | Hooks and openings | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-11-27 | X | ETH2D2-V04 | Hooks and openings | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |
| 2026-11-28 | Instagram | ETH2D2-V05 | Captions and editing craft | 17:00 | Pending human approval | 1200 / 3.5% / 6 / 1 |
| 2026-11-29 | YouTube Shorts | ETH2D2-V06 | Hooks and openings | 16:00 | Pending human approval | 1800 / 2.5% / 7 / 1 |
| 2026-11-30 | LinkedIn | ETH2D2-V07 | Captions and editing craft | 13:30 | Pending human approval | 900 / 3.0% / 5 / 1 |
| 2026-12-01 | X | ETH2D2-V08 | Hooks and openings | 14:00 | Pending human approval | 600 / 2.0% / 3 / 0 |